## INSTRUCTIONS
Financial planning of Interreg NEXT programmes (June 2021) ANNEX: Financial planning tool
PROGRAMME TIMELINE AND FINANCIAL FLOWS
The following tool was created by the TESIM project so that you can simulate different scenarios of the financial needs of your programme depending on the programme implementation timeline, financial committments and arrangements of the reporting and payments to the projects. The tool will provide you with the following outputs to support the decision making:
| - | Visualisation of the programme's implementation timeline
| - | Simulation of annual financial needs
| - | Visualisation of financial payments to the projects over the programme lifetime
| - | Estimations of annual and cumulative financial needs (per call / per year)
You can use any of the outputs separately. For example, you can use the visualisation of the programme's implementation timeline to discuss with your stakeholders the arrangements for calls and the implementation of the projects. For what concerns the financial estimations, you can use them to demonstrate how the implementation arrangements affect the annual financial needs and simulate different scenarios, depending on the size and timing of the payments to the projects. Likewise, you can use the estimations to benchmark whether the financial plan you have in mind does not possess any significant de-committment risks. Or use them any other way you find useful!
TECHNICAL INSTRUCTIONS:
For entering the data, please use Worksheet 'Input'.
White cells are input cells, the remaining of the worksheets are locked (no password; you can unprotect any worksheet).
Light orange cells on your right include the instructions.
For outputs, please see worksheets: - 'Graph 1 - Timeline' - Graph 2 - payment needs - 'Tables 1 -3: Payments to the projects'
In case you have any questions about formulas, assumptions or functionality, please contact: edmunds.snikeris@tesim-cbc.eu
A project funded by the European Union |  |  |  | Implemented by a consortium led by

## INPUT - Parameters
INPUTS
IMPLEMENTATION AND FINANCIAL MODALITIES OF THE PROGRAMME
|  | 1. Basic parameters |  |  |  |  | STEP 1 - Please enter the name of your programme, total budget and expected approval date!
|  | Name | Total budget | Programme approved by the EC
|  | South-Eastern-Nordic Programme | 60 million Eur | 2021-12-01
STEP 2 - Please breakdown your programme budget in EU and non-EU sources. Additionally, please identify the EU share in TA costs (D15) in Eur. Total costs have been calculated as 10% (but you can change the % in cells B 13 and B15) planned. Remember that total sums are calculated automatically, on the basis of your data!
2. Programme budget (Eur) parameters
|  | Eu funding | 54000000
|  | Other funding | 6000000
|  | Total funding | 60000000
|  | Funds available to the projects | Amount (Eur) | EU share (Eur)
|  | Allocation minus built-in EU TA flat rate | 55090909.0909 | 49090909.0909
Percentage for the funds for the Technical Assistance
|  | 10% - calculated as maximum available amount via built in flat rate | 4909090.9091 | 4909090.9091
STEP 3 - Please indicate the main parameters for planned calls (the % of the programme funds for each of the calls, up to three); if only one or two calls are planned, leave respective fields (C20 or C21) blank.
|  | 3. Parameters for calls for proposals | % of programme budget | Amount (Eur) | EU share (Eur) | Launch of the call
|  | 1st Call | 40% | 22036363.6364 | 19636363.6364 | 2022-05-01
|  | 2nd Call | 40% | 22036363.6364 | 19636363.6364 | 2023-03-01
|  | 3rd Call | 20% | 11018181.8182 | 9818181.8182 | 2024-01-01
|  |  | TOTAL | 55090909.0909 | 49090909.0909
[7 empty] | STEP 4 - Please indicate approx. % (from total budget) to be paid to the projects in each of the instalments. You can 'play with numbers' and model different scenarios (with pre-financing or without) to see how it will impact the financial needs on an annual basis. The model llows up to four payment simulation; if you allow for three payments (pre, interim, final) please leave the 1st or 2nd payment blank. |  | 2022-03-01
|  | 4. Parameters for payments to the project (approximations) | [6 empty] | 2022-04-01
|  |  | % of programme budget | [5 empty] | 2022-05-01
|  | Advance amount | 40% | [5 empty] | 2022-06-01
|  | 1st payment amount | 20% | [5 empty] | 2022-07-01
|  | 2nd payment | 20% | [5 empty] | 2022-08-01
|  | Final payment amount | 20% | [5 empty] | 2022-09-01
2022-10-01
[7 empty] | STEP 5 - Please identify the timeline for the calls for proposals and implementation of the projects. You are asked to indicate steps for the first call and similar timeline (length of each step) will be applied for other calls indicated in Step 3. The model is allows up to four payment simulations; if you allow three payments (pre, interim, final) please leave the 1st or 2nd payment blank. |  | 2022-11-01
|  | 5. Timeline parameters of the call for proposal/ projects | [6 empty] | 2022-12-01
|  |  | Duration | Timeline |  |  |  |  | 2023-01-01
| Call and contracting | Launch of the call | --- | 2022-05-01 |  |  |  |  | 2023-02-01
|  | End of the call | 3 months | 2022-07-01 |  |  |  |  | 2023-03-01
|  | Approval of the project by the MC | 8 months | 2023-03-01 |  |  |  |  | 2023-04-01
|  | Grant contracts signed (average for call) | 3 months | 2023-06-01 |  |  |  |  | 2023-05-01
|  | Advance payments to the projects | 1 month | 2023-07-01 | * Disbursement of funds |  |  |  | 2023-06-01
| 1st period | End of 1st reporting period | 9 months | 2024-03-01 |  |  |  |  | 2023-07-01
|  | Project progress reports recieved | 3 months | 2023-06-01 |  |  |  |  | 2023-08-01
|  | Management verifications/1st interim payments to the projects (average) | 3 months | 2024-09-01 | * Disbursement of funds |  |  |  | 2023-09-01
| 2nd period | End of 2nd reporting period | 9 months | 2024-12-01 |  |  |  |  | 2023-10-01
|  | Project progress reports recieved | 3 months | 2025-03-01 |  |  |  |  | 2023-11-01
|  | Management verifications/2nd interim payments to the projects (average) | 3 months | 2025-06-01 | * Disbursement of funds |  |  |  | 2023-12-01
| Final period | End of final reporting period | 9 months | 2025-09-01 |  |  |  |  | 2024-01-01
|  | Project progress reports recieved | 3 months | 2025-12-01 |  |  |  |  | 2024-02-01
|  | Management verifications/Final payments to the projects (average) | 3 months | 2026-03-01 | * Disbursement of funds |  |  |  | 2024-03-01
2024-04-01
|  | 6. Expected technical assistance spending per year |  |  |  |  | STEP 6 - Please estimate the approximate funds for the Technical assistance per year. |  | 2024-05-01
[5 empty] | CUMULATIVE |  |  |  | 2024-06-01
|  |  | Total amount (Eur) | EU share (Eur) | Total amount (Eur) | EU Share (Eur) |  |  | 2024-07-01
|  | 2021 | 409091 | 409091 | 409091 | 409091 |  |  | 2024-08-01
|  | 2022 | 818181.8333 | 818182 | 1227272.8333 | 1227273 |  |  | 2024-09-01
|  | 2023 | 818181.8333 | 818181.8333 | 2045454.6667 | 2045454.8333 |  |  | 2024-10-01
|  | 2024 | 818181.8333 | 818181.8333 | 2863636.5 | 2863636.6667 |  |  | 2024-11-01
|  | 2025 | 818181.8333 | 818181.8333 | 3681818.3333 | 3681818.5 |  |  | 2024-12-01
|  | 2026 | 818181.8333 | 818181.8333 | 4500000.1667 | 4500000.3333 |  |  | 2025-01-01
|  | 2027 | 409091 | 409091 | 4909091.1667 | 4909091.3333 |  |  | 2025-02-01
|  | TOTAL | 4909091.1667 | 4909091.3333 |  |  |  |  | 2025-03-01
2025-04-01
2025-05-01
STEP 7 - please proceed further to the following worksheets to the see the simulated timeline and size of annual financial needs on the programme level!
A project funded by the European Union | [7 empty] | Implemented by a consortium led by

## GRAPH 1 - Timeline
GRAPH 1: TIMELINE
The timeline is automatically updated, according to the time and duration defined in Step 5 (parameters for call for proposals/implementation).
A project funded by the European Union |  | Implemented by a consortium led by

## GRAPHS 2 to 4 - Payment needs
GRAPHICS
Graph 4 - Indicative timeline of payments to the projects
|  |  | 1st call | 2nd call |  | 3rd call
A project funded by the European Union |  |  |  |  | Implemented by a consortium led by

## TABLES 1-3 Payments to projects
TABLES 1-3: PAYMENTS TO PROJECTS
TABLE 1 presents the estimation of the payment needs of the programme during each year of implementation. Simulation of payments based on the timeline of the reporting (Parameter 5) and the approximate proportions of pre/interim/financial payments (Parameter 4), as well as expected TA amounts per year. Detailed breakdown please see below.
1. Payment needs of the programme (ANNUAL)
PROJECTS AND TECHNICAL ASSISTANCE
|  |  |  | Amount (Eur) | % of Total budget | EU share (Eur)
|  |  | 2021 | 409091 | 0.6818% | 409091
|  |  | 2022 | 818181.8333 | 1.364% | 818182
|  |  | 2023 | 9632727.2879 | 16.05% | 8672727.2879
|  |  | 2024 | 14040000.0152 | 23.4% | 12600000.0152
|  |  | 2025 | 14040000.0152 | 23.4% | 12600000.0152
|  |  | 2026 | 16243636.3788 | 27.07% | 14563636.3788
|  |  | 2027 | 4816363.7273 | 8.027% | 4336363.7273
|  |  | TOTAL | 60000000.2576 |  | 54000000.4242
TABLE 2 is the simulation of payments to the projects based on the timeline of the reporting (Parameter 5) and the approximate proportions of pre/interim/financial payments (Parameter 4). By changing parameters you can simulate various scenarious of how the procedural arrangements and beneficiary behavior affects the financial flow of the programme.
2. Expected disbursements from the programme to the projects (PER CALL / PER PERIOD).
|  |  |  | Time | Amount (Eur) | EU share (Eur)
|  | 1st Call | Advance | 2023-07-01 | 8814545.4545 | 7854545.4545
|  |  | 1st payments | 2024-09-01 | 4407272.7273 | 3927272.7273
|  |  | 2nd payments | 2025-06-01 | 4407272.7273 | 3927272.7273
|  |  | Final payments | 2026-03-01 | 4407272.7273 | 3927272.7273
|  | 2nd Call | Advance | 2024-05-01 | 8814545.4545 | 7854545.4545
|  |  | 1st payments | 2025-07-01 | 4407272.7273 | 3927272.7273
|  |  | 2nd payments | 2026-04-01 | 4407272.7273 | 3927272.7273
|  |  | Final payments | 2027-01-01 | 4407272.7273 | 3927272.7273
|  | 3rd Call | Advance | 2025-04-01 | 4407272.7273 | 3927272.7273
|  |  | 1st payments | 2026-06-01 | 2203636.3636 | 1963636.3636
|  |  | 2nd payments | 2027-03-01 | 2203636.3636 | 1963636.3636
|  |  | Final payments | 2027-12-01 | 2203636.3636 | 1963636.3636
TABLE 3 presents the estimation of the payment needs of the programme, cumulative for each year of implementation. The estimation is automatically calculated taking into account the timeline indentified in Step 5, as well as payment proportions identified in Step 4. Depending on the planned procedures you can simulate different scenarios!
3. Payment needs of the programme (CUMULATIVE)
PROJECTS AND TECHNICAL ASSISTANCE
|  |  |  | Amount (Eur) | % of Total budget | EU share (Eur)
|  |  | 2021 | 409091 | 0.6818% | 409091
|  |  | 2022 | 1227272.8333 | 2.045% | 1227273
|  |  | 2023 | 10860000.1212 | 18.1% | 9900000.2879
|  |  | 2024 | 24900000.1364 | 41.5% | 22500000.303
|  |  | 2025 | 38940000.1515 | 64.9% | 35100000.3182
|  |  | 2026 | 55183636.5303 | 91.97% | 49663636.697
|  |  | 2027 | 60000000.2576 | 100% | 54000000.4242
A project funded by the European Union | [7 empty] | Implemented by a consortium led by

## GRAPH 2 - PAYMENT NEEDS (hidden)
Timeline drop-down
2021-05-01
2021-06-01
2021-07-01
2021-08-01
2021-09-01
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
2024-03-01
2024-04-01
2024-05-01
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01
2026-02-01
2026-03-01
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01

## HIDDEN - DROP DOWN LISTS ETC (hidden)
Timeline drop-down |  |  |  | Value
2021-05-01 | Launch of the call | --- | 2022-05-01 | 1
2021-06-01 | End of the call | 3 months | 2022-07-01 | 1
2021-07-01 | Approval of the project by the MC | 8 months | 2023-03-01 | 1
2021-08-01 | Grant contracts signed (average for call) | 3 months | 2023-06-01 | 1
2021-09-01 | Advance payments to the projects | 1 month | 2023-07-01 | 1
| End of 1st reporting period | 9 months | 2024-03-01 | 5
2021-10-01 | Project progress reports recieved | 3 months | 2023-06-01 | 2
| Management verifications/1st interim payments to the projects (average) | 3 months | 2024-09-01 | 2
2021-11-01 | End of 2nd reporting period | 9 months | 2024-12-01 | 5
| Project progress reports recieved | 3 months | 2025-03-01 | 3
2021-12-01 | Management verifications/2nd interim payments to the projects (average) | 3 months | 2025-06-01 | 3
2022-01-01 | End of final reporting period | 9 months | 2025-09-01 | 5
2022-02-01 | Project progress reports recieved | 3 months | 2025-12-01 | 4
2022-03-01 | Management verifications/Final payments to the projects (average) | 3 months | 2026-03-01 | 4
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
2024-03-01
2024-04-01
2024-05-01
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01
2026-02-01
2026-03-01
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01
2028-03-01
2028-04-01
2028-05-01
2028-06-01
2028-07-01
2028-08-01
2028-09-01