## Risk profile
INHERENT RISK FACTORS OF THE PROJECT
Project identification
Short name
Inherent risk factors - risks associated with the project or the beneficiaries*
Inherent risk factors | Impact | Remarks of the PM
1. Project design and partnership
Project end date is close to 31 December 2022
Size of the partnership
Changes in the partnership
Type of the partnership
Risks identified by the project
2. Finance
Lead Beneficiary from Russia
Availability of own financing
Size of the project budget
Presence of State aid in the project
Increase of infrastructure costs
3. Activities and indicators
Significant contribution of the project towards programme indicators
Seasonal character of works for investment and research
4. Management, coordination and visibility
Exceeded deadlines set by the programme (reports, explanations, clarifications, additional documents, payment requests, etc.)
Communication with the JTS(including BOs)/MA and other communication
Overall risk level |  | Formula to be decided after all initial assessments done by the JTS
Overall risk profile | DEFAULT CONTROL MEASURES
Mandatory
Additional

## Risks
Risk matrix and control measures
Project title |  |  | Start Date
Lead Beneficiary |  |  | End Date
LB Country and address |  |  | Reporting period
Risk factors affecting project implementation | Risk category (intial) | Risk category (1st PR) | Previous control measures | Revised control measures | Dates of risk revision | Summary, comments from the PM
1. Project partnership and duration
Project end date is close to 31 December 2022 | Low
Size of the partnership | High
Changes in the partnership | Low
Type of the partnership | Medium
Risks identified by the project | High
2. Finance
Lead Beneficiary from Russia | Low
Availability of own financing | Medium
Size of the project budget | High
Presence of State aid in the project | Medium
Increase of infrastructure costs | Low
Existence of the ineligible costs in the EV certificate / progress reports (in addition, the AA reports) | N/A
Deviations between planned and reported costs per period | N/A
3. Activities and indicators
Significant contribution of the project towards programme indicators | Low
Seasonal character of works for investment and research | Low
Delay in implementation of project activities | N/A
Progress towards the achievement of the project and programme output indicators | N/A
Proposed changes in activities may concern achievement of project outputs and results | N/A
Management, coordination and visibility
Exceeded deadlines set by the programme (reports, explanations, clarifications, additional documents, payment requests, etc.) | Low
Communication with the JTS(including BOs)/MA and other communication | Low
Poor quality of reports (narrative section) | N/A
Visibility and communication to ensure the compliance with the programme visibility requirements | N/A
Risk score and category | [Low / medium / high]

## Risk criteria
RISK CRITERIA
1. Project design and partnership
Risk identified | Criteria | Inherent or on-going?
Project end date is close to 31 December 2022 | High – 1.10.2022 to 31.12.2022 Medium – 01.01.2022 to 30.09.2022 Low – until 31.12.2021 | Inherent and ongoing
Size of the partnership | High – 5 and more beneficiaries Medium – 3 to 4 beneficiaries Low – 2 beneficiaries | Inherent
Changes in the partnership | High – Change of the beneficiary (and/or lead) Medium – Change of an associated partner Low – No changes | Inherent and ongoing
Type of the partnership | High – at least one SME Medium – at least one NGO and/or universities Low – public entities | Inherent
Risks identified by the project | High – High impact and likelihood risks identified Medium – medium impact and likelihood risks identified Low – low impact and likelihood risks identified | Inherent
2. Finance
Risk identified | Criteria | Inherent or on-going?
Lead Beneficiary from Russia | High – yes Low - no | Inherent
Availability of own financing | High – in case of SMEs Medium - in case of NGOs and Russian public entities Low – in case of Estonian public entities During the project implementation, it has to be assessed according to the information available by the PM | Inherent and ongoing
Size of the project budget | High – Above 500 000 Medium – Between 100 000 and 500 000 Low – Less than 100 000 | Inherent
Presence of State aid in the project | High – GBER State aid Medium - de-minimis aid Low – No State aid | Inherent
Increase of infrastructure costs | High – significant infrastructure component with technical documentation* Medium – infrastructure component Low – no infrastructure *All LIPs by default high | Inherent and ongoing
Existence of the ineligible costs in the EV reports / reports | High – 2% and more of the reported costs Medium – up to 2% of the reported costs Low – no ineligible costs | Ongoing
Deviations between planned and reported costs per period | High – Changes more than 15% from the budget headings Medium – Deviations up to 15% from the budget headings Low – spending according to the plan, with minor deviations | Ongoing
3. Activities and indicators
Risk identified | Criteria | Inherent or on-going?
Significant contribution of the project towards programme indicators | High – (all LIPs), only one project delivering programme level indicator(s) Medium - several projects delivering programme level indicator(s) Low – many projects delivering programme level indicator(s) | Inherent
Seasonal character of works for investment and research | High – ‘Reserve season’ is not available for re-planning, if needed Medium - ‘Reserve season’ is available for re-planning, if needed Low - No works affected by seasonality | Inherent
Delay in implementation of project activities | High – delays in the procurement of infrastructure Medium – delays in any other activities Low – no or minor (within same reporting period) delays | Ongoing
Progress towards the achievement of the project and programme output indicators | High – Significant delays in the achievement of the indicators Medium – in general good progress, however achievement of some indicators is delayed Low – Steady progress towards the achievement of the indicators (time and content-wise) Assessment includes professional judgement of the PM carrying out progress report check. | Ongoing
Proposed changes in activities may concern achievement of project outputs and results | High – Major changes Medium – Minor changes Low – no changes All LIPs are assessed as high risk project by default | Ongoing
4. Management, coordination and visibility
Risk identified | Criteria | Inherent or on-going?
Exceeded deadlines set by the programme (reports, explanations, clarifications, additional documents, payment requests, etc.) | High – Repeated delays after extra deadline set from the programme Medium – not significant delays from the given deadline Low – No delays | Inherent and ongoing
Communication with the JTS(including BOs)/MA and other communication | High - significant/recurrent problems noticed Medium - some problems noticed Low – no problems noticed * information from the PM is the key (professional judgement based on the cooperation during the application, contracting and other stages) | Inherent and ongoing
Poor quality of reports | High – repeated clarifications (content-related), as well as disbalance between the spending and the project progress Medium – only technical corrections and minor clarifications, managed within set deadlines Low – no clarifications / only technical corrections, good balance between spending and the project progress | Ongoing
Visibility and communication to ensure the compliance with the programme visibility requirements | High – no evidence submitted, significant shortcomings of the visibility rules in the progress report Medium – some evidence obtained, Low – no breach of visibility rules after checks of the report | Ongoing